## Sprint 1 Backlog
Date | 2021-12-06 | Week Number | 3 | Group | 27
|  | Phase | 1
Priority |  | Author of the task | TODO | IN PROGRESS | UNDER TEST | DONE
Critical |  | All members (during meeting) | Analyse Jabref codebase |  |  | X | Priority Scale:
Critical |  | Pedro Simoes 58674 | Create github repository via forking |  |  | X | Critical - indispensable
Critical |  | All members (during meeting) | Elaborate the general use-case diagram |  |  | X | High - very important
High |  | Bruno Ramos 52886 | Elaborate the Database Organization UC diagram |  |  | X | Medium - required
High |  | Francisco Freire 58667 | Elaborate the Entry Collection UC diagram |  |  | X | Low - not required for now
High |  | Francisco Pires 58208 | Elaborate the File Sharing UC diagram |  |  | X
High |  | Pedro Simoes 58674 | Elaborate the Cite(Citation) UC diagram |  |  | X
High |  | Goncalo Vicencio 57944 | Elaborate the Configurations Organization UC diagram |  |  | X
Medium |  | Pedro Simoes 58674 | Peer Review Database Organization UC diagram |  |  | X
Medium |  | Bruno Ramos 52886 | Peer Review Entry Collection UC diagram |  |  | X
Medium |  | Francisco Freire 58667 | Peer Review File Sharing UC diagram |  |  | X
Medium |  | Francisco Pires 58208 | Peer Review Configurations Organization UC diagram |  |  | X
Medium |  | Goncalo Vicencio 57944 | Peer Review Cite(Citation) UC diagram |  |  | X
High |  | Respective author of each diagram | Elaborate the use-case description docx |  |  | X
Critical |  | All members (during meeting) | Manage remote repository |  |  | X
Critical |  | All members (during meeting) | Analyse Jabref codebase to find code smells |  |  | X
High |  | Each member is free to search anywhere in the codebase, keeping communication up, so that it doesn't overlap with others. | Elaborate the code-smell report documents |  |  | X
Medium |  | Francisco Freire 58667, Francisco Pires 58208, Goncalo Vicencio 57944 | Peer review Pedro's code-smell report documents |  |  | X
Medium |  | Francisco Pires 58208, Goncalo Vicencio 57944, Pedro Simoes 58674 | Peer review Bruno's code-smell report documents |  |  | X
Medium |  | Goncalo Vicencio 57944, Pedro Simoes 58674, Bruno Ramos 52886 | Peer review Francisco Freire's code-smell report documents |  |  | X
Medium |  | Francisco Freire 58667, Bruno Ramos 52886, Pedro Simoes 58674 | Peer review Francisco Pires code-smell report documents |  |  | X
Medium |  | Francisco Freire 58667, Bruno Ramos 52886, Francisco Pires 58208 | Peer review Goncalo's code-smell report documents |  |  | X
Critical |  | All members (during meeting) | Scrum Master Assignment |  |  | X
Medium |  | Bruno Ramos 52886 | Scrum Master Tasks |  |  | X
Critical |  | All members (during meeting) | Analyse Jabref codebase to find design patterns |  |  | X
High |  | Each member is free to search anywhere in the codebase, keeping communication up, so that it doesn't overlap with others. | Elaborate the design pattern report documents |  |  | X
Medium |  | Francisco Freire 58667, Francisco Pires 58208, Goncalo Vicencio 57944 | Peer review Pedro's design pattern report documents |  |  | X
Medium |  | Francisco Pires 58208, Goncalo Vicencio 57944, Pedro Simoes 58674 | Peer review Bruno's design pattern report documents |  |  | X
Medium |  | Goncalo Vicencio 57944, Pedro Simoes 58674, Bruno Ramos 52886 | Peer review Francisco Freire's design pattern report documents |  |  | X
Medium |  | Francisco Freire 58667, Bruno Ramos 52886, Pedro Simoes 58674 | Peer review Francisco Pires design pattern report documents |  |  | X
Medium |  | Francisco Freire 58667, Bruno Ramos 52886, Francisco Pires 58208 | Peer review Goncalo's code-smell report documents |  |  | X
Critical |  | All members (during meeting) | Manage remote repository |  |  | X
Critical |  | All members | Attend Planned Team meeting |  |  | X
Critical |  | All members (during meeting) | Structured Metrics Analysis |  |  | X
High |  | Francisco Freire 58667 | Chidamber-Kemerer Metrics report elaboration |  |  | X
High |  | Francisco Pires 58208 | Martin Packaging Metrics report elaboration |  |  | X
High |  | Pedro Simoes 58674 | Complexity Metrics report elaboration |  |  | X
High |  | Goncalo Vicencio 57944 | Lines of Code Metrics report elaboration |  |  | X
High |  | Bruno Ramos 52886, Francisco Pires 58208, Francisco Freire 28667 | MOOD Metrics report elaboration |  |  | X
Critical |  | All members (during meeting) | Manage remote repository |  |  | X
Critical |  | All members | Attend Planned Team meeting |  |  | X

## Sprint 2 Backlog
Date | Week Number |  | Group | 27
| Phase | 1
Priority | Author of the task | TODO | IN PROGRESS | UNDER TEST | DONE
Priority Scale:
Critical - indispensable
High - very important
Medium - required
Low - not required for now